## Sheet2
Date	Task
Monday Week 9 - Term 1	Submit Progress Report
Week 10 - Term 1	Server Implementation finished
Christmas Break - Week 1
Christmas Break - Week 2	P.C Client finished
Christmas Break - Week 3
Christmas Break - Week 4	Android Application finished
Week 1 - Term 2	Complete framework finished
Week 2 - Term 2
Week 3 - Term 2
Week 4 - Term 2	Implementation finished
Week 5 - Term 2
Week 6 - Term 2	Analysis finished
Week 7 - Term 2	Conclusion finished
Week 8 - Term 2	Further work finished
Week 9 - Term 2	Presentation finished
Week 10 - Term 2
Week 9 and Week 10 - Term 2	Project Presentations
Easter Break - Week 1
Easter Break - Week 2
Easter Break - Week 3
Easter Break - Week 4	Project Report finished
Easter Break - Week 5
Thursday Week 1 - Term 3	Submit Project Report